## Work Plan Samples
SAMPLE: ARPA Work Plan - Domestic Violence, Purpose Area 1
| Purpose Area 1: | Support the emergent needs of survivors who have been impacted by the COVID-19 public health emergency.
| Two Year Performance Date: | July 1, 2022 - June 30, 2024
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Enhanced supportive services for survivors that are safe and accessible where they need them most.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
1 | Provide emergency hotel stays for survivors and their children to reduce exposure to COVID-19. | Shelter Manager | Track 40, unduplicated, survivors and children who sheltered in a hotel for the two year period of this award, reporting results in the Semi-Annual Progress Report. | Emergency non non-congregate approaches to sheltering people to reduce exposure to COVID-19.. Survivor and their children provide feed back to Agency on the ease of the process in receiving emergency non-congregate shelter. | Agency survey will be completed by survivor reporting they feel safe. | Survivors report feeling safe.
2
SAMPLE: ARPA Work Plan - Domestic Violence, Purpose Area 2
| Purpose Area 2: | Assist with the transition to virtual, remote services, tele therapy and telehealth services, and assistance to survivors.
| Two Year Performance Date: | July 1, 2022 - June 30, 2024
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Safe voluntary access to virtual/remote and in-person services.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure (Project period is two years.)
1 | Provide training and/or access to virtual medical/ telehealth appointment for survivors to reduce exposure to COVID-19. | Counselor/Therapist | Track that 20 survivors were trained and/or provided access to a virtual medical/ telehealth appointment with Agency assistance, reporting results in the Semi-Annual Progress Report. | Survivor and their children will have virtual access to medical assistance. Survivors report gaining confidence in accessing virtual medical/ telehealth again in the future. | Agency survey will be completed by survivor reporting they received training and/or access to virtual medical/ telehealth appointment. | Survivors report "satisfied" at receiving trained and/or access to a virtual medical/ telehealth appointment with Agency assistance.
2
SAMPLE: ARPA Work Plan - Domestic Violence, Purpose Area 3
| Purpose Area 3: | Reduce the exposure to and risk of contracting the COVID-19 virus for survivors.
| Two Year Performance Date: | July 1, 2022 - June 30, 2024
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Reduced burden for programs that do not have resources and staff to support COVID-19 mitigation.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure (Project period is two years.)
1 | Provide 100 N-95 masks to all staff members, contractors, and survivors, to reduce exposure to COVID-19. | Shelter Manager | Track that 300 adult and 50 child N-95 masks have been provided to all staff members, contractors, and survivors for two years, reporting results in the Semi-Annual Progress Report. | Survivors report feeling safe after receiving services from your Agency. | Your Agency Initial Survey survivors, and periodic surveys to staff. | Survivors and Staff report "Organization has provided me with N-95 masks to reduce my exposure to COVID-19" and "satisfied" with receipt of N-95 masks distibuted to them.
2 | '' | '' | '' | '' | Your Agency Exit Survey to survivors states, and period survey to staff members. | Survivors and Staff report "I feel safer due to wearing an N-95 mask."
3
SAMPLE: ARPA Work Plan - Domestic Violence, Purpose Area 4
| Purpose Area 4: | Ensuring the continuity of programs and services during the COVID-19 public health emergency, which includes responding to issues such as adapting to fluctuating needs and changing circumstances.
| Two Year Performance Date: | July 1, 2022 - June 30, 2024
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Increased usage of mobile advocacy services for survivors. Mobile advocacy seeks to lower the barriers that prevent victim/survivors from accessing specialist domestic abuse support by offering a flexible outreach service.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
1 | Provide access to virtual support groups for survivors to reduce exposure to COVID-19. | Counselor/Therapist | 50 adults attended virtual support group meetings held weekly for 24 months | Survivors will attend virtual access support groups to assist in their recovery. Survivors report building support networks. | Survivors will complete an Agency survey after each group meeting. | Survivors report feeling "less isolated" as a result of the virtual support group meeting.
| HIGH LEVEL OUTCOME: | Enhanced supportive services for survivors that are safe and accessible where they need them most.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
4 | Provide transportation to survivors to access services that begin the healing process and reduce exposure to COVID-19 | Shelter Staff | Track that 100 trips have been provided to survivors to access legal, medical, or personal services, for two years, reporting results in the Semi-Annual Progress Report. | Vehicle report services they accessed began the healing process. | Your Agency vehicle Survey to survivors. | Survey may state "Transportation today allowed me to complete necessary activities to begin recovery process". Survivors report feeling "Satisfied" as a result transportation provided by your Agency..

## Additional Information
Additional Information
Performance Measurement, is a system for measuring the results of programs.
Why Performance Measurement? Performance measurement enables legislators, funding sources, and communities to understand what impact their dollars have had in a person's life, what change has resulted from dollars invested, or the effect on a community.
Performance Measurement, starts with the result in mind - what will occur if Activities are completed?
High Level Outcome: Overarching desired results of the Activity on the service area or target population your program is serving.
Activities: Provide the activity or initiative your Agency's staff will be performing that requires funding from this RFA. The Activity must be measurable, must be easy to track by Staff, and have the ability to be Evaluated.
Staff responsible: Provide the staff title of the person responsible for completing the Activity and collecting the survey or data for Evaluation.
Output: This is quantitative, the output can be measured, tracked and evaluated within the Program Performance Period. It can be the number of survivors served, number of services provided, or other measure. ( If you cannot measure and Activity, cannot collect data, or cannot Evaluate it, it is not an Output.)
Short Term Impacts: Interim progress in your Activities towards your High Level Outcome. Short-term impacts address change in your service area or target population as a result of the Activity.
Evaluation: Written documentation available for review that documents the condition of the survivor, service, or result after the Activity has been provided. Evaluation may utilize a survey, a financial document, a research-based instrument with demonstrated reliability and validity, interviews observations, records, a resulting change in Agency Policy and Procedures demonstrating a goal achievement, etc.
Virtual Services - The use of electronic devices, such as computers, tablets, and smartphones, to provide services for survivors through a secure platform. These services will enable domestic violence and sexual violence programs to support survivors and their children via an internet connection, web portal, and two-way live video platforms, https://telehealthresourcecenter.org/.

## Work Plan DV PA 1.)
ARPA Work Plan - Domestic Violence, Purpose Area 1
| Purpose Area 1: | Support the emergent needs of survivors who have been impacted by the COVID-19 public health emergency.
| Two Year Performance Period: | March 1, 2023 - February 28, 2025
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Enhanced supportive services for survivors that are safe and accessible where they need them most.
| HIGH LEVEL OUTCOME: | Increased access to health, wellbeing, and behavioral health supports for survivors and children.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
1
2
3

## Work Plan DV PA 2.)
ARPA Work Plan - Domestic Violence, Purpose Area 2
| Purpose Area 2: | Assist with the transition to virtual, remote services, tele therapy and telehealth services, and assistance to survivors.
| Two Year Performance Period: | March 1, 2023 - February 28, 2025
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Enhanced supportive services for survivors that are safe and accessible where they need them most.
| HIGH LEVEL OUTCOME: | Safe voluntary access to virtual/remote and in-person services.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
1
2
3

## Work Plan DV PA 3.)
ARPA Work Plan - Domestic Violence, Purpose Area 3
| Purpose Area 3: | Reduce the exposure to and risk of contracting the COVID-19 virus for survivors.
| Two Year Performance Period: | March 1, 2023 - February 28, 2025
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Enhanced supportive services for survivors that are safe and accessible where they need them most.
| HIGH LEVEL OUTCOME: | Reduced burden for programs that do not have resources and staff to support COVID-19 mitigation.
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
1
2
3

## Work Plan DV PA 4.)
ARPA Work Plan - Domestic Violence, Purpose Area 4
| Purpose Area 4: | Ensuring the continuity of programs and services during the COVID-19 public health emergency, which includes responding to issues such as adapting to fluctuating needs and changing circumstances.
| Two Year Performance Period: | July 1, 2022 - June 30, 2024
Program Name:
| Contract #: | FAM-22-082
| HIGH LEVEL OUTCOME: | Enhanced supportive services for survivors that are safe and accessible where they need them most.
| HIGH LEVEL OUTCOME: | Increased usage of mobile advocacy services for survivors. Mobile advocacy seeks to lower the barriers that prevent victim/survivors from accessing specialist domestic abuse support by offering a flexible outreach service
| Activity | Staff/Position Responsible | Output, must be a numbered measurement | Short Term Impact | Evaluation Method to Document Progress (Measure the short term impact of the activity.) | Outcome Measure
1
2
3